Summary

- Developer Hours:

Frontend Dev: 770 hrs (excluding map)

Backend Dev: 505 hrs (excluding map)

- QA Hours: 250 hrs

- PM Hours: 100 hrs

Start date: Jan 14, 2022

Deadline: April 5, 2022

Detailed Breakdown of Development Hours

- Frontend Estimation:   - 156hrs + 50hrs = 206hrs (For highlighted pages only)

- Style Guide  - 46hrs

    - Typography/ Branding and colors/ Icons setup - (6hrs)

    - Utility Classes - (6hrs)

    - Reusable Components - (34hrs)

      - Buttons

      - Links

      - Forms

      - Navigation

      - Mega Menu

      - Header

      - Footer

      - Offcanvas

      - Filter

  - Modules  - 78hrs

    - Above the fold - 6  (16hrs)

    - Cards - 10  (12hrs)

    - Slider - 2  (8hrs)

    - Sections  - 14  (42hrs)

  - Layout  - 32hrs

    - Homepage

    - Search result page

    - Contact

    - About

      - Team || Team bio page

      - Board

      - Funders and partners / Request form

      - Annual Report & Financials

    - Case for food

    - What we can do

- Become a service member

- What you’ll do

- Where you’ll work

- Career options after service

- Bring food corp to your district

- Change the system

- Policy Action Center

- Support our work

    - Donate

    - The skillet

      - The skillet news

      - The skillet stories

      - The skillet press

      - Lesson plans

      - Program guide

      - Article template

      - The skillet

    - Equity and Inclusion

    - Career

    - Partner with us

Responsive and Breakpoints

Animation + Image Mask Research : 50hrs

- Backend Estimation 115 hrs + ( 25hrs if subpages )

Global Components: 15 hrs

- Header - 8hrs

- Footer - 5 hrs

- Setup - 2 hrs

Pages: 100 hrs

- Homepage - 20 hrs

- Search result page - 15 hrs

- Contact - 8 hrs

- About - 8 hrs

  - Team || Team bio page - 11 hrs

  - Board - 6 hrs

  - Funders and partners / Request form - 22 Hrs

  - Annual Report & Financials - 10 Hrs

Batch 2

Detailed Breakdown of Development Hours

- Frontend Estimation:   - 176hrs + 32hrs = 208hrs

  - Modules  - 144hrs

    - Above the fold - 3  (12hrs)

    - Slider - 3  (12hrs)

    - Modules  - 23 (90hrs)

    - Re-use Modules - 16   (20hrs)

    - Form Modules (Donate Form) - 1  (10hrs)

  - Layout  - 32hrs

    - Donate

    - What You Can Do

    - Become a Service Member

    - Bring FoodCorps to Your District

    - Support Our Work

    - Career

    - Search

    - Partner With Us

Responsive and Breakpoints + Animation : 32hrs

Backend Estimation 108 hrs + ( 25hrs if subpages )

Pages: 108 hrs

- Donate

- What You Can Do - 6 hrs

- Become a Service Member - 40 hrs

- Bring FoodCorps to Your District - 22 hrs

- Support Our Work - 15 hrs

- Career - 20 hrs

- Search

- Partner With Us - 5 hrs

Batch 3

Detailed Breakdown of Development Hours

Frontend Estimation:   - 126hrs + 20hrs = 146hrs

  - Modules  - 94hrs

    - Above the fold - 1  (4hrs)

    - Slider - 1  (4hrs)

    - Modules  - 14 (56hrs)

    - Re-use Modules -18   (24hrs)

    - Shifting Module - 1  (6hrs)

  - Layout  - 32hrs

    - What You’ll Do (5-reuse) (1-new)

    - Where You'll Serve (1-reuse) (3-new)

      - Where You'll Serve Detail Page (8hrs)

    - After Service (2-reuse) (3-new)

    - Change the System (4-reuse) (1-new)

    - Policy Action Center (2-reuse) (1-new) (1-tab layouting)

    - Equity Inclusion (4-reuse) (2-new) (1-shifting module)

Responsive and Breakpoints + Animation : 20hrs

Backend Estimation  91 hrs + ( 15hrs if subpages )

Pages:  91hrs

- Policy Action Center - 16 hrs

- Change the System - 10 hrs

- What You’ll Do - 10 hrs

- Where We Work - 14 hrs ( excluding map, map estimation after map research )

- Site Detail Pages - 10 hrs

- Action for Equity Inclusion - 16 hrs

- After Service - 15 hrs

Ps: Map not included

Batch 4

Detailed Breakdown of Development Hours

Frontend Estimation:   - 190hrs + 20hrs = 210hrs

  - Modules  - 150hrs

    - Above the fold (4-hero variation) - 2  (12hrs)

    - Modules  - 27 (108hrs)

    - Re-use Modules -24 (38hrs)

  - Layout  - 32hrs

    - What We Do (5-reuse) (2-new)(1-FPO)

    - The Case for Food (Design to be provided)

    - The Skillet (7-reuse) (7-new) (1-tab layouting)

    - Impact (4-reuse) (3-new)

    - Program Guide (3-reuse) (2-new)

    - Article Template (1-reuse) (8-new) (4-hero variation)

    - Lesson Plan (4-reuse) (6-new)

Responsive and Breakpoints + Animation : 20hrs

Backend Estimation  100 hrs + ( 25hrs if subpages )

Pages:  hrs

- What We Do - 10 hrs

- The Case for Food - Cannot found design

- The Skillet - 40 hrs

- Impact - 11 hrs

- Program Guide - 14 hrs

- Article Template - 10 hrs

- Lesson Plans - 15 hrs

Ps: The Case for Food Design to be provided

Batch 4 Questions:

- Does these icons stack on mobile devices ?

- Do these Resources have a detailed page?

- Does this lesson plan have a detailed page? What file extension are users going to upload(eg: pdf)

- Does this video play in a popup model? What happens when we click on to ‘see the full list of videos’, does this link open the provided doc linked?

- Where does the season link to? Or is it only for listing?

- Can you please elaborate more on this section?